## WIP Schedule
Work in Process (WIP) Schedule
Company | Your company name |  |  | Yellow cells: type your numbers. White cells calculate on their own.
Month end | MM/DD/YYYY |  |  | Job A and Job B are the examples from our WIP guide. Type over them with your own jobs.
Free template from CFO Strategies. Guide: cfostrategiesllc.com/work-in-process-schedule/
YOU ENTER | [5 empty] | CALCULATED
Job # | Job name | Contract amount (with approved change orders) | Estimated total cost | Cost to date | Billed to date | Percent complete | Earned revenue | Over (under) billed | Estimated gross profit | Estimated gross profit % | Gross profit to date | Cost to complete | Revenue left to earn (backlog) | Notes
A | Job A (example) | 1000000 | 850000 | 425000 | 550000 | 50% | 500000 | 50000 | 150000 | 15% | 75000 | 425000 | 500000
B | Job B (example) | 600000 | 480000 | 360000 | 400000 | 75% | 450000 | -50000 | 120000 | 20% | 90000 | 120000 | 150000
Totals |  | 1600000 | 1330000 | 785000 | 950000 | 59.02% | 950000 | 0 | 270000 | 16.88% | 165000 | 545000 | 650000
|  |  |  | Total overbillings (a liability on the balance sheet) |  |  |  | 50000
|  |  |  | Total underbillings (an asset on the balance sheet) |  |  |  | 50000
|  |  |  | Net over (under) billed |  |  |  | 0
Read the WIP one row at a time. In the example, the totals net to zero, but Job A is $50,000 overbilled and Job B is $50,000 underbilled.
Numbers in Job A and Job B are for illustration only.
Note on C7: The full contract value, including change orders the owner has approved.
Note on D7: Update this every month with the project manager. Do not just take budget minus cost from the system.
Note on G7: Cost to date divided by estimated total cost (the cost-to-cost method).
Note on I7: Billed to date minus earned revenue. Over: billed ahead of the work. Under: work not billed yet.

## How to Use
How to use this WIP schedule
A work in process (WIP) schedule shows, job by job, what each contract is worth, what it has cost so far, how much revenue you have earned, how much you have billed and how much profit you expect to make.
Steps
1. Type your company name and the month-end date at the top of the WIP Schedule tab.
2. Use one row for each open job. Fill in the yellow cells: contract amount (with approved change orders), estimated total cost, cost to date from job costing, and billed to date.
3. Leave the white cells alone. They calculate on their own.
4. Update it every month with your financial statements, so it ties to them.
5. Read it one row at a time, not just the totals.
What each calculated column means
Percent complete | Cost to date divided by estimated total cost (the cost-to-cost method).
Earned revenue | Contract amount times percent complete.
Over (under) billed | Billed to date minus earned revenue. Overbilled means you billed ahead of the work: a liability, and the cash should still be in the bank. Underbilled means work you have not billed yet: an asset, but often a sign of an unapproved change order, a late billing or costs running over.
Estimated gross profit | Contract amount minus estimated total cost, for the whole job.
Estimated gross profit % | Estimated gross profit divided by the contract amount.
Gross profit to date | Earned revenue minus cost to date.
Cost to complete | Estimated total cost minus cost to date. Get this from the project manager each month rather than trusting the budget math in your accounting system.
Revenue left to earn (backlog) | Contract amount minus earned revenue: the revenue still ahead on the job.
Notes | Flags a job whose cost to date is already over its estimate, or whose estimate shows a loss.
Loss jobs
When a job's estimated total cost is higher than its contract amount, the job is expected to lose money. Talk to your accountant about how to record it: the whole expected loss is usually recorded as soon as it is known, not spread over the rest of the job.
Learn more
The Construction WIP Schedule: How to Read It, With an Example
Over/Under Billing Calculator (check one job in seconds)
Want help with your WIP?
CFO Strategies builds and updates the WIP every month as part of your monthly financial reporting, and reviews it with you and your project managers.
Book a free consultation: cfostrategiesllc.com/contact-us/ or call (855) 732-7861
This template is for general information and is not accounting or tax advice.